## TaskList
Task ID | Task Name | Description | Priority | Assigned To | Status
T-001 | Setup project repository | Initialize Git repo and create branch structure | High | Alex | Done
T-002 | Design database schema | Create ERD and define table relationships | High | Alex | Done
T-003 | Create user authentication | Implement login/logout and password reset | High | Michael | In Progress
T-004 | Build landing page | Design and code responsive landing page | Medium | Sandy | In Progress
T-005 | Setup CI/CD pipeline | Configure automated testing and deployment | High | Tracy | In Review
T-006 | Write API documentation | Document all endpoints with examples | Medium | Alex | In Review
T-007 | Create user dashboard | Build main dashboard with analytics widgets | High | Sandy | In Progress
T-008 | Implement search feature | Add full-text search with filters | Medium | Alex | In Review
T-009 | Design email templates | Create transactional email designs | Low | Tracy | In Review
T-010 | Add payment integration | Integrate Stripe for subscriptions | High | Michael | In Review
T-011 | Build notification system | Real-time notifications via WebSocket | Medium | Sandy | In Progress
T-012 | Create admin panel | Admin dashboard for user management | Medium | Tracy | In Progress
T-013 | Implement dark mode | Add theme toggle with dark/light modes | Low | Alex | Backlog
T-014 | Write unit tests | Achieve 80% code coverage | High | Michael | Backlog
T-015 | Performance optimization | Reduce page load time under 2 seconds | Medium | Sandy | Backlog
T-016 | Mobile responsiveness | Ensure all pages work on mobile devices | High | Tracy | To Do
T-017 | User onboarding flow | Create guided tour for new users | Medium | Alex | Backlog
T-018 | Export data feature | Allow users to export data as CSV/PDF | Low | Sandy | Backlog
T-019 | Accessibility audit | Ensure WCAG 2.1 compliance | Medium | Alex | In Progress
T-020 | Security review | Conduct penetration testing and fix issues | High | Tracy | In Review
T-021 | Implement file upload | Add drag-and-drop file upload functionality | High | Michael | In Review
T-022 | Create reporting module | Build customizable report generation system | High | Sandy | In Progress
T-023 | Add two-factor auth | Implement 2FA using SMS or authenticator app | High | Alex | In Review
T-024 | Build user profile page | Allow users to edit profile and preferences | Medium | Tracy | In Review
T-025 | Implement rate limiting | Add API rate limiting to prevent abuse | High | Alex | In Progress
T-026 | Create backup system | Automated daily backups with restore option | High | Tracy | In Progress
T-027 | Add data validation | Implement form validation across all inputs | Medium | Alex | In Review
T-028 | Build activity log | Track and display user activity history | Medium | Tracy | In Review
T-029 | Implement caching layer | Add Redis caching for improved performance | High | Michael | In Review
T-030 | Create help center | Build FAQ and documentation pages | Low | Alex | Done
T-031 | Add bulk import feature | Allow CSV/Excel bulk data import | Medium | Tracy | In Progress
T-032 | Implement webhooks | Create webhook system for integrations | Medium | Alex | In Review
T-033 | Build team management | Add team creation and member management | High | Tracy | In Review
T-034 | Create audit trail | Log all data changes for compliance | High | Michael | In Progress
T-035 | Add localization support | Implement multi-language support | Medium | Sandy | In Progress
T-036 | Build API versioning | Implement versioned API endpoints | Medium | Alex | In Progress
T-037 | Create data archiving | Archive old records to improve performance | Low | Alex | In Progress
T-038 | Implement SSO login | Add Single Sign-On with OAuth providers | High | Alex | In Progress
T-039 | Build custom fields | Allow users to create custom data fields | Medium | Tracy | To Do
T-040 | Add session management | View and revoke active sessions | Medium | Michael | Backlog
T-041 | Create API sandbox | Build sandbox environment for API testing | Low | Sandy | Backlog
T-042 | Implement data encryption | Encrypt sensitive data at rest | High | Alex | Backlog
T-043 | Build role permissions | Granular role-based access control | High | Tracy | Backlog
T-044 | Add scheduled tasks | Allow users to schedule recurring tasks | Medium | Michael | Backlog
T-045 | Create status page | Public service status and uptime page | Low | Sandy | To Do
T-046 | Implement soft delete | Add trash/restore functionality | Medium | Alex | Backlog
T-047 | Build integration hub | Connect with third-party services | High | Tracy | Backlog
T-048 | Add comment system | Allow comments on tasks and items | Medium | Michael | Backlog
T-049 | Create user analytics | Track user engagement metrics | Medium | Sandy | Backlog
T-050 | Implement GDPR tools | Data export and deletion requests | High | Alex | Backlog

## KanBan Board
Assigned To | Alex | Priority
Backlog | In Progress | In Review | Done
Implement dark mode | Accessibility audit | Write API documentation | Setup project repository
User onboarding flow | Implement rate limiting | Implement search feature | Design database schema
Implement data encryption | Build API versioning | Add two-factor auth | Create help center
Implement soft delete | Create data archiving | Add data validation
Implement GDPR tools | Implement SSO login | Implement webhooks